# Project: Emotion Detection Platform
Objective: Cloud-based system that classifies speaker emotions in audio/video per sentence, accessible via Web UI, API, and CLI
 Tech: Python, FastAPI, Docker, Azure ML, Streamlit, GitHub Actions

Key Deliverables: CLI tool, Web App, REST API, Azure-hosted training, documentation, peer-reviewed logs, final demo

CREATIVE BRIEF

| Name | Role / Focus Area | Responsibility |
| --- | --- | --- |
|  | DevOps / Azure | Azure ML setup, CI/CD pipelines, Dockerization, deployment, monitoring |
|  | Backend (CLI + Model) | Refactor PoC to modules, develop CLI, integrate inference and training logic |
|  | API Developer | Create FastAPI endpoints for training/inference, add security/authentication |
|  | Frontend (UI + Streamlit/Gradio) | Build Streamlit UI, connect to API, visualize emotions |
|  | Docs + QA | Write unit/integration tests, document APIs, logs, model usage, peer reviews |

Each member must log their contribution and assigned role in their learning log. (ILO 1.8: Professional practice, ILO 2.8: Emotional awareness and personal development)

WEEK 1 (May 7–9): Kickoff, Planning, Setup

Goal: Set up tools, define structure, align on tasks

ILO Coverage: 1.8 (Professional Practice), 2.8 (Emotional Intelligence)

- ILO 1.8: Submitting professional-standard work, code practices, structured collaboration

- ILO 2.8: Team coordination, personal goal setting, self-awareness in communication

### User Stories

- As a team member, I want to know what I’m building and how we’ll build it so that I can contribute effectively.

- As a group, we want to prepare tooling and shared resources, so we are productive from the next sprint onward

### Daily Tasks

May 7 (Wed)

- Create GitHub repo, define main and dev, set .gitignore, README.md

- Agree on tools: Python, FastAPI, Streamlit/Gradio, Azure ML, Docker

- Set up Azure Boards and write initial backlog/epics

- DataLab self-study

May 8 (Thu)

- Plan out src/ package structure (modules: cli, model, training, inference)

- Create and share instructions for venv setup

- Everyone: Create individual branches for their focus areas

- DataLab self-study

May 9 (Fri)

- Write shared document outlining goals, deliverables, roles

- Finalize task list for Sprint 2 (starting May 13)

- Move key PoC components into a new model.py module as preparation

- DataLab self-study

WEEK 2–3 (May 13–24): CLI + API MVP

Goal: Build the CLI and local API for inference with basic logging and unit testing

ILO Coverage: 9.3, 9.5, 8.9, 10.3, 1.8

- ILO 9.3: Writing high-quality production-ready code with logging, docstrings, structure

- ILO 9.5: Local deployment and packaging of inference logic using containers and GitHub workflows

- ILO 8.9: Training/testing ML models locally with automation support

- ILO 10.3: Visualizing results via API responses for external consumption

- ILO 1.8: Consistent professionalism in code structure and collaboration

Sprint 2 Deliverables: Working CLI, FastAPI, Docker container, initial test coverage

### User Stories

- As a researcher, I want to run emotion detection from the command line for local testing and batch processing.

- As an engineer, I want an API so that other apps (like the UI) can access model predictions remotely.

Week 2 (May 13–17) – CLI First

May 13 (Mon)

- Start CLI structure using argparse or click

- Write test plan + setup pytest

May 14 (Tue)

- Link CLI to predict() from PoC

- Add input validation, logging, and test cases

May 15 (Wed)

- Add loguru or logging, log key events

- Run initial tests, provide feedback

May 16 (Thu)

- Write Dockerfile for CLI

- Package the CLI and test in Docker

May 17 (Fri)

- Run CLI end-to-end test on local files

- Document CLI usage in README

### Week 3 (May 20–24) – Build Local API

May 20 (Mon)

- Start FastAPI app: /predict, /health

- Write OpenAPI schema with pydantic

May 21 (Tue)

- Connect API to inference logic

- Refactor shared predict.py used by both CLI and API

May 22 (Wed)

- Dockerize API and compose both API and CLI containers

- Write integration tests using httpx

May 23 (Thu)

- Add input validation, audio file handling

- Set up local docker-compose for full stack testing

May 24 (Fri)

- End-to-end test: Audio → API → Response

- Finalize Sprint 2 docs and coverage reports

WEEK 4–5 (May 27–June 7): Azure ML + Web UI

Goal: Deploy model training pipeline in Azure and build user-friendly front-end
Sprint 3 Deliverables: Azure ML training, registered model, web app connected to API

ILO Coverage: 9.4, 8.9, 10.3, 1.8

- ILO 9.4: Implementing data pipelines using industry standards, data versioning and cloud storage

- ILO 8.9: Training on cloud platforms with reproducible pipelines and environment control

- ILO 10.3: Visualizing model results for stakeholders in a functional interface

- ILO 1.8: Maintaining professional project documentation and accountability

### User Stories

- As a developer, I want to train our model on Azure with versioned data so I can compare improvements.

- As a user, I want a website where I can upload a file and get emotion predictions per sentence.

### Week 4 (May 27–31) – Azure ML Setup + Pipeline

May 27–28 (Mon–Tue)

- Set up Azure ML workspace + register dataset

- Write training pipeline (data → preprocess → train → evaluate)

May 29–31 (Wed–Fri)

- Register model + environment in Azure

- Enable model versioning, connect to inference function

- Write Azure training documentation

### Week 5 (June 3–7) – Build the Web UI

June 3 (Mon)

- Build Streamlit/Gradio app for uploading audio

- Expose API endpoint for web use

June 4–5 (Tue–Wed)

- Connect frontend to API

- Style UI, show emotion + confidence visualizations

June 6–7 (Thu–Fri)

- Test full flow: Upload → Predict → Display

- Collect screenshots for documentation

## WEEK 6–7 (June 10–21): Deploy to Azure, Monitor, CI/CD

Goal: Finalize backend infra, secure deployment, enable monitoring
Sprint 4 Deliverables: Azure-hosted app, model monitoring, CI/CD, secure API (Deploy)

ILO Coverage: 9.5, 10.3, 9.4, 4.4, 1.8

- ILO 9.5: Deploying full stack ML pipelines with automated retraining and monitoring

- ILO 10.3: Monitoring dashboards and data tracing for performance analysis

- ILO 9.4: Automation and scheduling of data processing workflows

- ILO 4.4: Designing a scalable architecture and estimating cost-efficient cloud solutions

- ILO 1.8: Final stage professional behavior, documentation, handoff quality

### User Stories

- As a project owner, I want our app deployed and monitored so I can ensure reliability and performance.

- As a user, I want secure access to model predictions without worrying about server downtime.

### Week 6 (June 10–14) – CI/CD + Deployment

June 10–12 (Mon–Wed)

- Set up GitHub Actions to deploy on push

- Add auth token to API (header-based or OAuth)

- Improve CLI install (pip install ., .whl)

June 13–14 (Thu–Fri)

- Add Azure Application Insights

- Monitor logs, set up basic alerts

- Document deployment architecture

### Week 7 (June 17–21) – Finalize App

June 17–19 (Mon–Wed)

- Polish UI design

- Enable /train and /evaluate routes (stub)

- Run performance tests (latency, response time)

June 20–21 (Thu–Fri)

- Freeze features all code and infra stable

- Host documentation on GitHub Pages

- Project is considered done

WEEK 8 (June 24–27): Final Testing, Demo, Submission

Goal: Prepare evidence, finalize docs, demo the product
Sprint 5 deliverables: Poster, final repo, .whl, Azure link, logs

ILO Coverage: All ILOs, especially 1.8, 2.8, 10.3

- ILO 1.8: Work quality across team artifacts, reflective behavior and peer review

- ILO 2.8: Team collaboration, feedback loops, peer assessment and logs

- ILO 10.3: Poster, frontend demos, final presentation clarity to stakeholders

### User Stories

- As a student, I want to demonstrate the complete workflow so I can show what we built.

- As an assessor, I want to see your product, understand how it works, and read clear docs.

### June 24–25 (Mon–Tue)

- Create demo walkthrough: Upload → Emotion Analysis

- Finalize sprint reports, peer reviews

- Finalize user guide, API docs, usage examples

- Build and print poster

- Back up Docker + Azure deployments

### June 26 (Wed)

- Submit:

  - GitHub repo + README

  - .whl file + pip install instructions

  - Link to hosted app (API/UI)

  - Logs, peer reviews, demo video/poster

  - Documentations

  - Poster

### June 27 (Thu)

DEMO + SUBMISSION DAY

- Attend demo session, answer Q&A, show off app

## Final Deliverables (Due June 27)

- CLI Tool (cli.py, .whl) — ILO 9.3: Production-ready code, ILO 9.5: Deployment-ready inference logic

- REST API (FastAPI) — ILO 9.5: Deployable model endpoints, ILO 10.3: External interfaces for stakeholders

- Frontend UI (Streamlit/Gradio) — ILO 10.3: Visual storytelling of results

- Azure ML Pipeline + Versioned Model — ILO 9.4: Data pipeline and training, ILO 8.9: Cloud ML

- Azure-hosted App with CI/CD + Monitoring — ILO 9.5: Monitoring + auto deploy, ILO 4.4: Architecture + budgeting

- Architecture Diagram, Cost Evaluation, Monitoring Logs — ILO 4.4: Cloud architecture reasoning

- Peer Reviews, Learning Logs, Work Logs — ILO 1.8: Professional work logs, ILO 2.8: Emotional/self-reflection

- Final Poster + Demo Presentation — ILO 10.3: Presentation + visualization for stakeholders